## IT Risk Assessment Matrix
IT RISK ASSESSMENT MATRIX TEMPLATE
REF/ID | RISK TYPE | ASSET | RISK DESCRIPTION | RISK SEVERITY | RISK LIKELIHOOD | INTERNAL IMPACT | USER IMPACT | TRIGGER | MITIGATIONS / REMEDIES | ASSET | RISK SEVERITY KEY | RISK LIKELIHOOD KEY | RISK LEVEL KEY
| Estimation | TRUSTED INSIDER | A member overestimating their skills to finish part of the code in relation to time. | TOLERABLE | IMPROBABLE | LOW | LOW | If a member's inexpeince conflicts with their ego, this could occur. | Keep individual egos from flaring up. | EXTERNAL | ACCEPTABLE | IMPROBABLE | LOW
| Organizational | TRUSTED INSIDER | Members have unstructured work and go off on tangents that aren't tasks. Possible lack of Management. | UNDESIRABLE | POSSIBLE | HIGH | MEDIUM | If members are not focused and management cannot retain focus, this can occur. | Have a person the members respect as a manager. | INSIDER | TOLERABLE | POSSIBLE | MEDIUM
| People | TRUSTED INSIDER | A member refuses to do tasks or finish them on time. | INTOLERABLE | IMPROBABLE | HIGH | HIGH | If a member feels slighted or antagonistic, this can occur. | Foster an inclusive environment where people feel that they are rewarded for work. | TRUSTED INSIDER | UNDESIRABLE | PROBABLE | HIGH
| Requirements | EXTERNAL | The C.E.O. decides to implement a new requirement that has to be worked around. | TOLERABLE | POSSIBLE | EXTREME | HIGH | If the CEO wants to add a twist in the project, this will occur. | Just hope it dosen't happen. Also keep code flexable to accomodate any changes. |  | INTOLERABLE |  | EXTREME
| Technology | EXTERNAL | One or more members lose internet access. | TOLERABLE | POSSIBLE | MEDIUM | MEDIUM | If there is a large storm or power outage, this may occur. | Consitantly save to cloud so minimal changes are lost.
| Tools | EXTERNAL | A manager has trouble configuring project tools. | ACCEPTABLE | PROBABLE | LOW | LOW | If a manager is new to a tool, this can occur. | Spend a little extra time getting used to the new tool.
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.